## Slide 1
CAPITAL PROGRAM FUNDING OUTLOOK
LAND DEVELOPMENT COMMITTEE
October 16, 2014
Jerry Marchbank
Senior Director, Facilities, Planning, and Construction

## Slide 2: Discussion
Capital Improvement Program (CIP) Background
Recent Funding Impacts
Immediate Facility Needs
Campus Outlook
“The New Reality”
Next Steps

## Slide 3
  Vision 2020 Funding Need (2011):
  Total CIP Program Cost: $965.3M
  State Funding (anticipated): $193.0M
  Local Funding Need: $772.3M
  Measure M (2012):
  Provides $698M in local funds
    72.3% of total program cost
    90.4% of anticipated local funding need
CIP Funding Background:

## Slide 4: CIP Funding Background (cont.):
  Program was never fully-funded;
  Projected funding gap would be supplemented by:
    1) Interest earnings;
    2) Leveraging more external funding;
    3) Accelerating the program schedule to reduce impact of escalation.
        What is the value of a day?
        (3.5%/365) x $698,000,000 = $67,000 per day

## Slide 5: Recent Funding Impacts:
  Interest Earnings
    0.427% in County Treasury -- $539,644 (6/30/14)
  Leveraging more external funding
    No State-wide Education Bond in 2014 and a 2016 bond is unlikely
  Accelerating schedule to reduce impact of escalation
    The CEQA process was scheduled to conclude in July 2014 and will likely not conclude until April/May 2015

## Slide 6: Immediate Facility Needs:
  GWC Science/Mathematics Building
    This project seeks to build a new 111,000 square foot instructional building to replace the existing Math/Science building built in 1966. This project has been GWC’s top project priority since the 2006-2007 planning year.
    Estimated Project Cost: $82.9M State-funded: $53.9M
  OCC Language Arts & Social Sciences (IDC, Phase II)
  This project seeks to build a new 107,000 square foot instruction building to house language arts, behavioral and social sciences, and humanities classes. This project has been approved for state-funding since 2009.
  Estimated Project Cost: $71.1M State-funded: $41.2M

## Slide 7: Campus Outlook:
  Coastline College: CCC does not anticipate advancing any projects from the State-funding queue. The campus Facilities and Planning committee will meet to discuss project priorities.
  Golden West College: GWC intends to move forward with construction of the Math/Science Building. It is likely that the new Business/Social Science building, anticipated to commence in 2022, will not have sufficient funding.
  Orange Coast College: OCC intends to move forward with construction of the Language Arts & Social Sciences building (IDC, Phase II). The Facilities & Planning Committee has voted to deprioritize the proposed Parking Structure and Administration projects in lieu of advancing the IDC project immediately.

## Slide 8
  Vision 2020 Funding Need (2014):
  Total CIP Program Cost: $975.7M
    $18.1M increase, mitigated to $10.4M
  State Funding (anticipated): $99.9M
  Local Funding Need: $875.8M
  Measure M (2012):
  Provides $698M in local funds
    71.5% of total program cost
    79.8% of anticipated local funding need
The New Reality:

## Slide 9: Next Steps:
  Move forward with OCC IDC and GWC Math/Science projects as supported by the campus governance committees;
  Revise CIP schedule in anticipation of state funding in 2018, but prepare project proposals to be “in queue” for 2016;
  Continue to work with campus shared governance groups to evaluate project priorities and budget saving opportunities;
  Mitigate effects of escalation, to the extent possible, through advanced project planning;
  Maximize outside funding sources (i.e. Prop 39, SMSR, Utility Incentives) to the greatest extent possible.